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Project Updates
Date: December 12, 2023
To: Chairman and Members of the Planning and Zoning Commission
From: Susy Victor-Trevino, Planning Manager 
Subject: Current Project Updates in the City of Saginaw, Texas	
______________________________________________________________________________
Background/Discussion:
Please see below the latest updates for current projects in the City, please note dates are subject to change:

1. Alpine at the Square
a. In Progress: 
i. Dirt work and building pad construction.
ii. Sanitary sewer (10% complete)
b. Scheduled Completion Date: 6/30/25

2. Beltmill Booster Pump
a. In Progress: City Punch list was accepted

3. Beltmill Cottages
a. 100% Complete: Concrete, including Wagley Robertson
b. Scheduled Completion Dates: 
i. Entire Project: 02/05/24 
ii. Wagley Robertson Paving: 01/15/24
iii. Traffic Signals in Service By: 03/01/24

4. Beltmill Villas
a. Complete: Paving and All Utilities
b. Utilities Scheduled Completion Date: TBD

5. Cement Creek Drainage 
a. Complete: City has issued final acceptance letter.

6. Cement Creek Phase II
a. Start of Construction: 12/11/23
b. 30% Complete 
c. Scheduled Completion Date: 04/15/24
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Project Updates (Continued)

7. Foodliner
a. Complete: Public Utilities
b. In Progress: Contractor is finishing with the building 
c. Scheduled Completion Date: 02/15/25 (Building Structure)

8. Kiwanis Veterans Memorial Relocation
a. 100% Complete: Utilities and structure
b. In Progress: Contractor is working on the final inspection punch list
c. Scheduled Completion Date: 02/01/24

9. Knowles Drive Phase 1
a. Complete: Waiting on the contractor to complete the required paperwork for close out.
10. Knowles Reconstruction (Phase II)
a. Start Date: 09/20/23
b. Contract Time: 120 days out of 735 used
c. Complete: Water and Storm Drain for Fossil Wood, paving subgrade
d. In progress: Paving to begin on 1/22/2024
e. Scheduled Completion Date: Mid-March 2024

11. Knowles Reconstruction (Phase III)
a. Scheduled Start Date: After Phase II is open to traffic.

12. Northwest Booster Pump
a. In Progress: Waiting for contractor to replace the roof that was damaged during transport and for Oncor to run power to pump station.
b. Scheduled Completion Date: 2/15/2024

13. Saginaw Library
a. 100% Complete: Sanitary sewer and drainage (final inspection scheduled on 12/07/23)

14. Senior Living Phase III
a. 100% Complete: Utilities
b. In Progress: Contractor started dirt work for the site and building.
c. Scheduled Completion Date: 01/15/24

15. Taco Bueno Restaurant
a. Waiting on the final paper work before final acceptance.
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Project Updates (Continued)

16. Tricon Saginaw 
a. 100% Complete: Public Utilities
b. In Progress: Concrete Paving
d. Scheduled Paving Date: 4/15/2024

**All information received and confirmed by Bill Hurst, Senior Inspection Manager.
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