Project Updates

Date: December 12, 2023

To: Chairman and Members of the Planning and Zoning Commission

From: Susy Victor-Trevino, Planning Manager

Subject: Current Project Updates in the City of Saginaw, Texas

______________________________________________________________________________

Background/Discussion:

Please see below the latest updates for current projects in the City, please note dates are subject to change:

- Alpine at the Square

  - In Progress:

    - Dirt work and building pad construction.

    - Sanitary sewer (10% complete)

  - Scheduled Completion Date: 6/30/25

- Beltmill Booster Pump

  - In Progress: City Punch list was accepted

- Beltmill Cottages

  - 100% Complete: Concrete, including Wagley Robertson

  - Scheduled Completion Dates:

    - Entire Project: 02/05/24

    - Wagley Robertson Paving: 01/15/24

    - Traffic Signals in Service By: 03/01/24

- Beltmill Villas

  - Complete: Paving and All Utilities

  - Utilities Scheduled Completion Date: TBD

- Cement Creek Drainage

  - Complete: City has issued final acceptance letter.

- Cement Creek Phase II

  - Start of Construction: 12/11/23

  - 30% Complete

  - Scheduled Completion Date: 04/15/24

Project Updates (Continued)

- Foodliner

  - Complete: Public Utilities

  - In Progress: Contractor is finishing with the building

  - Scheduled Completion Date: 02/15/25 (Building Structure)

- Kiwanis Veterans Memorial Relocation

  - 100% Complete: Utilities and structure

  - In Progress: Contractor is working on the final inspection punch list

  - Scheduled Completion Date: 02/01/24

- Knowles Drive Phase 1

  - Complete: Waiting on the contractor to complete the required paperwork for close out.

- Knowles Reconstruction (Phase II)

  - Start Date: 09/20/23

  - Contract Time: 120 days out of 735 used

  - Complete: Water and Storm Drain for Fossil Wood, paving subgrade

  - In progress: Paving to begin on 1/22/2024

  - Scheduled Completion Date: Mid-March 2024

- Knowles Reconstruction (Phase III)

  - Scheduled Start Date: After Phase II is open to traffic.

- Northwest Booster Pump

  - In Progress: Waiting for contractor to replace the roof that was damaged during transport and for Oncor to run power to pump station.

  - Scheduled Completion Date: 2/15/2024

- Saginaw Library

  - 100% Complete: Sanitary sewer and drainage (final inspection scheduled on 12/07/23)

- Senior Living Phase III

  - 100% Complete: Utilities

  - In Progress: Contractor started dirt work for the site and building.

  - Scheduled Completion Date: 01/15/24

- Taco Bueno Restaurant

  - Waiting on the final paper work before final acceptance.

Project Updates (Continued)

- Tricon Saginaw

  - 100% Complete: Public Utilities

  - In Progress: Concrete Paving

  - Scheduled Paving Date: 4/15/2024

**All information received and confirmed by Bill Hurst, Senior Inspection Manager.